## Product Backlog
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | As an unregistered website user I want to register as a regular user so that I can have an account |  | high | 3 |  | DoD 1# | i hate How Unorganised This Class Is | 1# Definition of Done
2 | As an unregistered website user I want to register as a publisher user so that I can add new titles |  | high | 3 |  | DoD 1# |  | 1) Code is peer reviewed
3 | As admin user I want to approve every requested publisher account so that I can verify the validity |  | high | 6 |  | DoD 1# |  | 2) Unit Tests Passed
4 | As a registered user I want to log into the website so that I can have a personalised experience |  | high | 2 |  | DoD 1# |  | 3) Meets acceptance criteria
5 | As a publisher user I want to log into the website so that I can see the publisher dashboard |  | high | 2 |  | DoD 1# |  | 4) Working on common browsers (Google Chrome, Mozilla Firefox, Microsoft Edge, Safari)
6 | As an admin I want to log into the website so that I can keep it running smoothly |  | high | 2 |  | DoD 1# |  | 5) Usability review conducted
7 | As a user, I want to search up authors so that I can buy more books written by that author |  | medium | 13 |  | DoD 1#
8 | As a user, I want to search for book titles so that I can rate it and write a review |  | medium | 13 |  | DoD 1#
9 | As a customer, I want to be able to look at my order history, so that I can keep track of my transactions |  | medium | 8 |  | DoD 1#
10 | as a customer, i want to be sent a notification, so that i know that my book order is canceled |  | medium | 20 |  | DoD 1#
11 | As a customer I want to cancel an order so that I can get my money back |  | medium | 8 |  | DoD 1#
12 | as a admin, i want to access the business dashboard so that i can monitor business activity |  | low | 8 |  | DoD 1#
13 | as a site customer i want to be sent an invoice so that i can make sure the purchase occured |  | low | 20 |  | DoD 1#
14 | as a site customer. i want to add books to the cart so that i can make multiple purchases |  | medium | 8 |  | DoD 1#
15 | As an admin, I want to be able to cancel an order, So that I can prevent certain stock from being sold |  | low | 3 |  | DoD 1#
18 | as a site user, i want to read reviews on books, so that i can judge what books i may want to read/purchase |  | low | 5 |  | DoD 1#
19 | As a customer, I want to view a books details, so that I can get a better understanding of it before I purchase it. |  | low | 5 |  | DoD 1#
21 | As a user, I want to search for book titles so that I can get information on a specific book |  | medium | 13 |  | DoD 1#
24 | As an admin i want to be able to add books so that the customers will have more choices when buying them |  | high | 5 |  | DoD 1#
25 | As a paying customer, i want to use paypal for payment, so that i can used my saved details |  | medium | 20 |  | DoD 1#
26 | As a customer, I want to be able to look at my transaction history so that I can check which orders I have previously cancelled |  | medium | 3 |  | DoD 1#
27 | as a site user, i want to add reviews to a book, so that i can share my thoughts on the product |  | low | 10 |  | DoD 1#
30 | As an admin, I want to be able to upload a books details, so that customers can view it |  | high | 5 |  | DoD 1#
31 | As a user, I want to view the books table of contents, so that I can gauge whether its suitable for me |  | medium | 5 |  | DoD 1#
32 | As an admin, I want to be able to upload pdf files, so that users can view the books contents |  | low | 3 |  | DoD 1#
33 | As a user, I want to access information about the website, so that I can learn more about the business and what the website can offer me |  | low | 1 |  | DoD 1#
34 | As a user, I want to contact the admin team, so that I can ask questions about signing up. |  | low | 1 |  | DoD 1#
35 | As a logged-in user, I want to list my book for sale, so that other users can purchase it |  | medium | 6 |  | DoD 1#
36 | As a user, I want to identify books in a certain category, so that I can find books relevant to my interests |  | medium | 3 |  | DoD 1#
37 | As a user, I want to look up a book by its ISBN, so that I can quickly and accurately find the specific book I am looking for |  | high | 3 |  | DoD 1#
38 | As an admin, I want to have a log of all the past transactions, so that I can keep track of what titles are popular |  | medium | 8 |  | DoD 1#
39 | As an admin I want to be able to block users so that I won't have unused accounts on my database |  | high | 4 |  | DoD 1#

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #NAME?
| Previous Year | #REF! | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | As an unregistered website user I want to register as a regular user so that I can have an account | #N/A | #N/A | #N/A | #N/A | #N/A
2 | As an unregistered website user I want to register as a publisher user so that I can add new titles | #N/A | #N/A | #N/A | #N/A | #N/A
3 | As admin user I want to approve every requested publisher account so that I can verify the validity | #N/A | #N/A | #N/A | #N/A | #N/A
4 | As a registered user I want to log into the website so that I can have a personalised experience | #N/A | #N/A | #N/A | #N/A | #N/A
5 | As a publisher user I want to log into the website so that I can see the publisher dashboard | #N/A | #N/A | #N/A | #N/A | #N/A
6 | As a user, I want to search up authors so that I can buy more books written by that author | #N/A | #N/A | #N/A | #N/A | #N/A
7 | As a user, I want to search for book titles so that I can rate it and write a review | #N/A | #N/A | #N/A | #N/A | #N/A
8 | As a customer, I want to be able to look at my order history, so that I can keep track of my transactions | #N/A | #N/A | #N/A | #N/A | #N/A
9 | as a customer, i want to be sent a notification, so that i know that my book order is canceled | #N/A | #N/A | #N/A | #N/A | #N/A
10 | As a customer I want to cancel an order so that I can get my money back | #N/A | #N/A | #N/A | #N/A | #N/A
11 | as a admin, i want to access the business dashboard so that i can monitor business activity | #N/A | #N/A | #N/A | #N/A | #N/A
12 | as a site customer i want to be sent an invoice so that i can make sure the purchase occured | #N/A | #N/A | #N/A | #N/A | #N/A
13 | as a site customer. i want to add books to the cart so that i can make multiple purchases | #N/A | #N/A | #N/A | #N/A | #N/A
14 | As an admin, I want to be able to cancel an order, So that I can prevent certain stock from being sold | #N/A | #N/A | #N/A | #N/A | #N/A
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | as a site user, i want to read reviews on books, so that i can judge what books i may want to read/purchase | #N/A | #N/A | #N/A | #N/A | #N/A
18 | As a customer, I want to view a books details, so that I can get a better understanding of it before I purchase it. | #N/A | #N/A | #N/A | #N/A | #N/A
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | As a user, I want to search for book titles so that I can get information on a specific book | #N/A | #N/A | #N/A | #N/A | #N/A
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 | As an admin i want to be able to add books so that the customers will have more choices when buying them | #N/A | #N/A | #N/A | #N/A | #N/A
24 | As a paying customer, i want to use paypal for payment, so that i can used my saved details | #N/A | #N/A | #N/A | #N/A | #N/A
25 | As a customer, I want to be able to look at my transaction history so that I can check which orders I have previously cancelled | #N/A | #N/A | #N/A | #N/A | #N/A