## Product Backlog
SPRINT #1 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
1 | As an unregistered website user I want to register as a regular user so that I can have an account | 1.1 | Create sign up page | Kyrice | X
|  | 1.2 | create error page, if details are invalid | Kyrice | X
|  | 1.3 | create success page if details are valid | Noel | X
|  | 1.4 | add a 'sign up' button to log in page | Kyrice | X
2 | As a registered user I want to log into the website so that I can have a personalised experience | 2.1 | Create a log in page | Kyrice | X
|  | 2.2 | Create a user specific home page | Noel | X
|  | 2.3 | create error page, if details did not match | Kyrice | X
X
3 | As a publisher user I want to log into the website so that I can see the publisher dashboard | 3.1 | create publisher log in functionality | Kyrice | X
|  | 3.2 | create a unique publisher dashboard | Noel | X
|  | 3.3 | create error page in case details do not match for the publisher | Kyrice | X
X
4 | As admin user I want to approve every requested publisher account so that I can verify the validity | 4.1 | create page for requested publisher accounts that are lodged | victoria | X
|  | 4.2 | give only admin user the rights to this approve/unnaprove process | victoria | X
|  | 4.3 | create a middlewear for the admin user to control other frontend data | tim | X
X
5 | As an admin I want to log into the website so that I can keep it running smoothly | 5.1 | create admin sign in on main sign up page | nandini | X |  |  | (or decide to create an admin portal sign in)
X
6 | As an unregistered website user I want to register as a publisher user so that I can add new titles | 6.1 | create a unique publisher sign-up form so that extra details can be taken at sign up in order to approve/unnaprove the publisher account | Kyrice | X

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | As an unregistered website user I want to register as a regular user so that I can have an account | #N/A | #N/A | #N/A | #N/A | #N/A
2 |  | #N/A | #N/A | #N/A | #N/A | #N/A
3 |  | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 |  | #N/A | #N/A | #N/A | #N/A | #N/A
7 | As a registered user I want to log into the website so that I can have a personalised experience | #N/A | #N/A | #N/A | #N/A | #N/A
8 |  | #N/A | #N/A | #N/A | #N/A | #N/A
9 |  | #N/A | #N/A | #N/A | #N/A | #N/A
10 |  | #N/A | #N/A | #N/A | #N/A | #N/A
11 | As a publisher user I want to log into the website so that I can see the publisher dashboard | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 |  | #N/A | #N/A | #N/A | #N/A | #N/A
14 |  | #N/A | #N/A | #N/A | #N/A | #N/A
15 | As admin user I want to approve every requested publisher account so that I can verify the validity | #N/A | #N/A | #N/A | #N/A | #N/A
16 |  | #N/A | #N/A | #N/A | #N/A | #N/A
17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 | As an admin I want to log into the website so that I can keep it running smoothly | #N/A | #N/A | #N/A | #N/A | #N/A
20 |  | #N/A | #N/A | #N/A | #N/A | #N/A
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 | As an unregistered website user I want to register as a publisher user so that I can add new titles | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A